## LandingRegisterLogin
If more functional tests are required we can add them to this document going forward. | [10 empty] | PLEASE WATCH ME!!
Test ID | Page | Description | Preconditions | Steps to Reproduce | Expected Result | Actual Result | Tester One Notes | Tester One | Tester Two | Tester Two Notes Round 2 | Testing Video
T-1 | Register | New user registration | Database running; user email is not in system | 1. Navigate to /register.jsp 2. Fill form with valid data 3. Click Register | User record created in DB; redirect to confirmation | Pass | User record created in DB, but rerouted to Reservation page with no indication of login status | Kypton | SE | Updated functionality. User record is created in db. User receices appropriate confirmation of account creation or that email already exists, and that user should go to the login page. note: When successful, registering should navigate to landing page, not stay on register page. ( update needed for final product) | Testing video one
T-3 | Login | Valid login | User exists with correct credentials | 1. Go to /login.jsp 2. Enter valid credentials 3. Click Login | Redirects to reservation.jsp; session created | Pass | Unsure if successful. It did reroute to the reservation page, but I am not sure if I have a user session going or not. Need to update with a confirmation that login was successful/indicate current login status somewhere during session. | Kypton | SE | User is shown successful or failuer to login dependingo on credentials used. | testing video one
T-2 | Register | Duplicate email validation | Existing user in DB already | 1. Attempt registration using same email 2. Submit form | Error message shown; no new record created | Pass | No new record created in DB, but rerouted to Reservation page with no error message or prompt for user to try different login information | Kypton | SE | Updated functionality. User record is created in db. User receices appropriate confirmation of account creation or that email already exists, and that user should go to the login page. | testing video two
T-4 | Login | Invalid login credentials | Valid email but wrong password | 1. Go to /login.jsp 2. Enter wrong password 3. Click Login | Displays 'Invalid email or password'; stays on login page | Pass | Flash image appears under Navigation bar | Kypton | SE | TO DO: Correct styling , add styled banner | testing video two
T-5 | Home / Landing | Landing Page for viewing | Database running | 1.Navigate to /home.jsp 2. page loads 3. View styling | Displays the main page, the images, and 5 buttons under the navigation bar. | Pass | Able to view the landing/ home page. | Kypton | SE
T-6 | Home / Landing | Test Navigation | Guest and exisiting Users can click on the buttons | 1. Click Reserve a room text button 2. click See Attractions text button 3. click Start booking text button 4. Click Explore text button 5. Click Find Reservation Button | Each text button will navigate to a different page. | Pass | All Navigation bar and Landing buttons are operating correctly. | Kypton | SE | TODO: correct Registration nav to reservation page. | Test Video three
Word Doc with images